Earned Value Management (EVM) is used in project management to measure project performance and progress by comparing planned work with actual work and cost.

Below is a typical numerical example often asked in exams.

Example Numerical

A project has the following data:

- Planned Value (PV) = $10,000

- Actual Cost (AC) = $12,000

- Earned Value (EV) = $8,000

Calculate:

- Cost Variance (CV)

- Schedule Variance (SV)

- Cost Performance Index (CPI)

- Schedule Performance Index (SPI)

Step 1: Formulas

- Cost Variance (CV) = EV − AC

- Schedule Variance (SV) = EV − PV

- Cost Performance Index (CPI) = EV / AC

- Schedule Performance Index (SPI) = EV / PV

Step 2: Calculations

1️⃣ Cost Variance (CV)
CV = 8000 − 12000
CV = −4000

➡ Negative CV means project is over budget.

2️⃣ Schedule Variance (SV)
SV = 8000 − 10000
SV = −2000

➡ Negative SV means project is behind schedule.

3️⃣ Cost Performance Index (CPI)
CPI = 8000 / 12000
CPI = 0.67

➡ CPI < 1 means cost efficiency is poor.

4️⃣ Schedule Performance Index (SPI)
SPI = 8000 / 10000
SPI = 0.8

➡ SPI < 1 means project progress is slower than planned.

✅ Final Results

| Metric | Result | Meaning |
| --- | --- | --- |
| CV | −4000 | Over budget |
| SV | −2000 | Behind schedule |
| CPI | 0.67 | Poor cost efficiency |
| SPI | 0.8 | Slow progress |

💡 Quick exam tip:

- Negative variance = problem

- Index < 1 = bad performance

- Index > 1 = good performance

Here are 5 solved numericals of Earned Value Management (EVM) commonly asked in project management exams.

1️⃣ Numerical 1

Given:

- Planned Value (PV) = $15,000

- Earned Value (EV) = $12,000

- Actual Cost (AC) = $13,500

Find:

CV, SV, CPI, SPI

Solution

Cost Variance (CV)
CV = EV − AC
CV = 12000 − 13500
CV = −1500

Schedule Variance (SV)
SV = EV − PV
SV = 12000 − 15000
SV = −3000

Cost Performance Index (CPI)
CPI = EV / AC
CPI = 12000 / 13500
CPI = 0.89

Schedule Performance Index (SPI)
SPI = EV / PV
SPI = 12000 / 15000
SPI = 0.8

✅ Project is over budget and behind schedule.

2️⃣ Numerical 2

Given:

- PV = $20,000

- EV = $22,000

- AC = $21,000

Solution

CV = EV − AC
CV = 22000 − 21000
CV = +1000

SV = EV − PV
SV = 22000 − 20000
SV = +2000

CPI = EV / AC
CPI = 22000 / 21000
CPI = 1.05

SPI = EV / PV
SPI = 22000 / 20000
SPI = 1.10

✅ Project is under budget and ahead of schedule.

3️⃣ Numerical 3

Given:

- PV = $18,000

- EV = $15,000

- AC = $16,000

Solution

CV = EV − AC
CV = 15000 − 16000
CV = −1000

SV = EV − PV
SV = 15000 − 18000
SV = −3000

CPI = EV / AC
CPI = 15000 / 16000
CPI = 0.94

SPI = EV / PV
SPI = 15000 / 18000
SPI = 0.83

✅ Project is over budget and behind schedule.

4️⃣ Numerical 4

Given:

- PV = $25,000

- EV = $24,000

- AC = $20,000

Solution

CV = EV − AC
CV = 24000 − 20000
CV = +4000

SV = EV − PV
SV = 24000 − 25000
SV = −1000

CPI = EV / AC
CPI = 24000 / 20000
CPI = 1.2

SPI = EV / PV
SPI = 24000 / 25000
SPI = 0.96

✅ Project is under budget but slightly behind schedule.

5️⃣ Numerical 5

Given:

- PV = $30,000

- EV = $27,000

- AC = $25,000

Solution

CV = EV − AC
CV = 27000 − 25000
CV = +2000

SV = EV − PV
SV = 27000 − 30000
SV = −3000

CPI = EV / AC
CPI = 27000 / 25000
CPI = 1.08

SPI = EV / PV
SPI = 27000 / 30000
SPI = 0.90

✅ Project is under budget but behind schedule.

📌 Important Formulas (Remember for exams)

- CV = EV − AC

- SV = EV − PV

- CPI = EV / AC

- SPI = EV / PV

⭐ Quick interpretation trick

| Result | Meaning |
| --- | --- |
| CV > 0 | Under budget |
| CV < 0 | Over budget |
| SV > 0 | Ahead of schedule |
| SV < 0 | Behind schedule |
| CPI > 1 | Good cost performance |
| SPI > 1 | Good schedule performance |

.